## Sheet1
Project | Task | Responsible | Accountable | Consulted | Informed | Scheduled Completion | Actual Completion | Steps/Remediation Plan
General | Build/Configure central repository for all <company> policies and procedures | Customer 1 |  |  |  | 2025-10-10 |  | Confluence/Archer/Service Now Any type of centralized documentation Repository
General | Build initial list of all documentation and templates needed | Customer 1 |  | Scott |  | 2025-10-10
General | Write Standard Operating Procedure for every 6 month documentation review. | Customer 1 |  |  |  | 2025-10-10
SOCII | Policies for Security Defined | Customer 1 |  | Scott |  |  |  | 1. System Acceptable Use Policy (AUP) deployed.
SOCII | Policies for Availability Defined | Customer 1 |  | Scott |  |  |  | 1. Business Impact Analysis conducted 2. Business Continuity Plan written 3. Disaster Recovery Plan written
SOCII | Policies for Privacy Defined | Customer 1 |  | Scott |  |  |  | 1. Policy for data handling and marking
SOCII | Policies for Confidentiality Defined | Customer 1 |  | Scott
SOCII | Policies for Processing Integrity Defined | Customer 1 |  | Scott
SOCII | Training Plan | Scott |  | Customer 1 |  | 2025-11-30 |  | How often do we train users? Virtual/In Person Tracking compliance training is complete Keeping users engaged with security "SWAG".
SOCII | Engage third party auditor | <vendor> |  | Scott Customer 1 |  | 2025-11-30 |  | Get initial assesment for how long an audit takes and then know when they must be engaged by.
ISO27001 | Initiation and Planning | [6 empty] | Framework mapping and checklist from NIST: https://csrc.nist.gov/projects/olir/informative-reference-catalog/details?referenceId=154#/ https://www.razil.io/post/nist-csf-2-0-to-iso-27001-2022-annexure-a-mapping
ISO27001 | Context and Risk Assessment | [6 empty] | https://csrc.nist.gov/projects/risk-management/about-rmf 1. Conduct a risk assessment: Formal, checklist 2. Develop Risk Treatment Plan 3. Create a statement of applicability (SoA): Controls to justify risk choices
ISO27001
ISO27001
ISO27001 | Engage 3rd Party Auditor |  |  |  |  | 2025-11-30 |  | Get initial assesment for how long an audit takes and then know when they must be engaged by.